## table 1_checklist
Review Period: Dates |  | Updated: 5.29.14
Reviewer: Stanley E. "Chip" Parrott, Bureau of Reclamation, Sacramento, CA
NOT FOR DISTRIBUTION - FOR INFORMATION PURPOSES ONLY
Table 1. Checklist of Required Information
Required Information | Meets Requirement(s) | Comments | Response to Information Requested | 5.27.14 Reclamation Responses to Additional Information Provided | Consultant Response to Information Requested | 5.29.14 Agency Responses to Information Requested
Transfer proposal | (Received 4/4/14) | Note:Seller's 2014 Water Transfer proposal (Proposal) cites DWR's 2013 Transfer Water Agreement Exhibit 1 (Exhibit 1) as including relevant technical details that also pertain to Seller's Proposal. In this checklist, items from Exhibit 1 are referenced including Figure 1, Table 1 and Table 3. Also, the missing, or required additional information is shown in BOLD below. |  | 5/23/14: Rec'vd. additional information as requested from Seller.
Notice and information requirements described in local ordinances | Incomplete | The Proposal states Seller has informed the the County of its proposed 2014 Water Transfer. The appropriate documentation from correspondence with the County will be provided to Reclamation when it becomes available. | See attached email dated May 7, 2014. | Rec'vd. email dated May 7, 2014 from Andy Hitchings. Seller satisfies the requirement. | - | -
Well ID: owner, owner ID, and district ID number | Incomplete | Up to 22 groundwater wells on Seller's Property are proposed to be pumped for the 2014 Water Transfer. Of these, 20 wells are identified on Table 1 of Exhibit 1. Well IDs are needed for the two proposed additional wells that are to be constructed and operated for the 2014 transfer. | Seller has indicated an additional groundwater well is proposed for use in the 2014 Water Transfer; and thus, up to 23 groundwater wells may be operated for the 2014 Water Transfer. The Well IDs for the additional proposed wells (to be constructed) are 12W5, 12W2 and 24W1, as shown on the attached updated map and Exhibit. | Well IDs of the three proposed additional transfer wells were provided in a revised Draft Exhibit 1. Seller satisfies the requirement. There are 2 well names in the 2014 Exhibit 1, Table 1 that do not match the well names given in the 2014 project map. The 2 well names in question are listed as 13W-5 and 21W-5 in table 1, but are shown as 13W-3 and 21W-3 in the map, respectively. In the 2013 Water Transfer, the well names that were used were 13W-3 and 21W-3. The well names in the 2014 Water Transfer should be consistent with the 2013 Water Transfer and conveyance agreement. | Please see the revised updated Exhibit 1 , Table 1. | Table has been corrected, Seller satisfies requirement
Well Location: a. Lat/Long., T,R,S; b. Well(s) shown on scaled, detailed map showing surface water features within 2 miles of service area boundary. Include wells in monitoring network. | a. Incomplete b. Incomplete | a. Lat/Long. well coordinates provided for 20 of the proposed 22 transfer wells and all proposed monitoring wells; T, R, S provided for 20 of the proposed 22 transfer wells. This information is required for the proposed two additional wells. b. Scaled map (Figure 1) shows 20 of the proposed 22 transfer wells, surface water features within 2 miles of the service area boundary, and wells in the monitoring network. The two proposed additional transfer wells must be added to Figure 1. | Please see the updated 2014 Water Transfer map and Exhibit. The following are the descriptions for the additional groundwater wells: 12W-2 (S13, T9N, R2E), 12W-5 (S6, T9N, R3E) and 24W-1 (S24, T9N, R2E). | Lat./Long. and T, R, S provided for each of the three proposed additional transfer wells. Seller satisfies the requirement. | - | -
Historic Operations: Volume of water pumped from each well in previous year. Document and identify areas normally irrigated by wells involved in the transfer. | Incomplete | For clarification, the Agencies request a simple spreadsheet providing updated, supporting documentation for the estimated 2014 baseline groundwater pumping for each of the proposed 22 transfer wells. This simple spreadsheet is needed to clarify the following information for each proposed well: 1) Based on an email from Consultant Eng., dated 5/8/14, Item A. indicates 7,633 AF of baseline pumping for participating wells during July-Sept. 2013. Please list the estimated baseline for each proposed well that documents this baseline volume of 7,633 AF. Also, in an email dated 5/18/14, Consultant provided estimates of monthly pumping during April-June 2013. On the same spreadsheet as above, please provide an updated listing (ie., without April pumping) of the estimated baseline pumping for May, June and also October 2013. In summary, the Agencies request a simple spreadsheet showing current estimates of 2014 baseline pumping at each proposed transfer well for the period May-October 2014. The proposal states on p. 2, "These proposed wells will be operated to pump groundwater into Seller’s conveyance system for irrigation deliveries to fields." | Please see the attached spreadsheet with the current 2014 baseline pumping quantities for May through October. | The spreadsheet submitted did not show October GW pumping baseline volumes. Please provide. DWR agrees, Seller needs to provide October pumping baseline volumes. Based on the 2013 Water Transfer Groundwater Data Electronic Reporting Forms, they may have not pumped in October of 2013. Also, DWR noticed a small error in the baseline (Well 31W-1 for June 2013) that would increase the baseline amount by 3 acre-feet. Call to discuss if needed. | No groundwater was pumped at Seller during the month of October. Please see the revised baseline spreadsheet which shows no October pumping as well as the correction in June for 31W-1. | Seller satisfies requirement.
Proposed Operations: a. Projected operation and beneficial use; b. Verification that totalizing flow meters installed and calibrated | a. Yes b. No | a) Seller proposes to use up to 22 pumping wells to make surface available for transfer by groundwater substitution during April - Oct. 2014; beneficial use: irrigation. b) The Proposal states flow meter calibrations and installations for thirteen of the proposed 22 wells remain active for the proposed 2014 Water Transfer. Flow meter calibration certifications for seven of the proposed pumping wells have recently been received, reviewed and approved by Reclamation and DWR. (Note: the information provided on the recently received calibration reports were compared to field notes taken by DWR staff (Tad Bedegrew) from the 2013 Water Transfer field visit.) Finally, flow meter calibration and installation certifications for the proposed two additional transfer wells are needed. | The flow meter calibration and installation certifications for the three proposed additional wells will be provided to Reclamation following construction of the wells and installation of the flow meters. | Pending
Well Construction | Incomplete | DWR Well Completion Reports (WCRs) are needed for the following wells as required by California Water Code Section 13751: 6W2, 20W1 and 21W3. Also, the depth of the annular surface seals were not reported for wells 6W2, 7W1, 20W1, 21W3 and 31W1. Annular surface seals for irrigation wells are required to be a minimum of 20 feet below ground surface (California Well Standards Bulletin 74-90, p. 23). Accordingly, based on the inadequate information provided, the following wells do not meet the DTIWT1 Appendix B Well Acceptance Criteria: 6W2, 7W1, 20W1, 21W3 and 31W1. | Reclamation staff (Sheri Looper) has identified that the groundwater wells approved for use in the 2013 Water Transfer will be allowed for use in the 2014 Water Transfer. Thus, we believe no further action is necessary relative to this item. | USBR technical did not approve these five wells for transfer (6W2, 7W1, 20W1, 21W3 and 31W1) based on the reasons provided under this requirement. However, USBR management has agreed to accept these wells. (Note: Well construction information is needed for the three additional wells.) | Well construction information will be provided for the three additional wells as it becomes available. | Pending
Geologic Log | Incomplete | WCRs showing a geologic log are required for the following wells: 6W2, 20W1, 21W3 and 31W1. | See response immediately above. | See response immediately above. (Note: Geologic logs are needed for the three additional wells.) | Geologic logs will be provided for the three additional wells as they become available. | Pending
Estimated Well Capacity and method | Incomplete | Estimated well capacity and the method for determining the capacity for 20 of the 22 proposed transfer wells was provided. This information is needed for the two additional transfer wells proposed to be constructed. | The capacities of the additional proposed wells will be provided to Reclamation as soon as the information becomes available. | Pending
Additional Information: Well pump efficiency test, pumping tests, groundwater quality data, site-specific studies | Incomplete | Either well pump efficiency test or constant-rate pumping test results were provided for 20 of the 22 proposed transfer wells. No groundwater quality or site-specific studies were submitted. |  | --
Pump Power: Verification that pump powered by electric source or offsetting reductions provided elsewhere | Incomplete | Exhibit 1, Table 1 shows 16 of the 20 transfer wells on Table 1 are electric-powered, the remaining 4 wells are diesel-powered 8W1, 8W2, 16W2 and 17W3. Copies of the diesel engine registrations from the Air Pollution Control District were provided for Seller's 2013 water transfer - these registrations are valid through December 2014. Also, the source of the pump power is needed for the two additional wells to be constructed. Finally, Seller needs to ensure that adequate air quality mitigation measures are taken to keep pollution levels below the thresholds specified in the 2014 Final EA/FONSI. | The source of power for the additional proposed wells to be constructed will be provided to Reclamation as soon as the information becomes available. In the case that the souirce of power is not electric, Seller will evaluate the emissions to ensure these remain within the thresholds identified in the EA/FONSI. The EA/FONSI identifies that Seller's four existing groundwater wells powered by diesel engines are within the threshold of identified for the requirements. | The revised Draft Exhibit 1 shows that the source of the pump power for the three proposed additional transfer wells is electric. Seller satisfies the requirement.
Groundwater Substitution Transfer Monitoring Plan
Required Elements of Plan | Meets Requirement(s) | Comments |  | Reclamation Responses to Additional Information Provided
Monitoring well network | Incomplete | Figure 1 in Exhibit 1 shows 10 monitoring well (MW) locations. Table 3 in Exhibit 1 lists 9 “Seller” MWs and 8 DWR MWs. Some of these wells are listed as single-completion wells while others are multi-level completion wells. Two "DWR" monitoring wells that were also used for the Seller 2013 Water Transfer were actually destroyed prior to the 2013 Water Transfer so should be removed from Seller's MW network. MW with SWN of 08N03E04R001M was destroyed in 2012 and MW with SWN of 10N02E12R001M was destroyed in 2010. The proposed MW network generally provides satisfactory areal coverage to the west and northeast of the proposed transfer wells. However, there is inadequate areal coverage north and southeast of the proposed transfer wells. DWR installed MWs during the early 1990s located just north and east of the seller's boundaries. DWR is not certain of the condition of these wells, but recommends Seller further investigate potentially using these wells in their monitoring network. With regard to vertical monitoring of the aquifer within the area of influence of the proposed pumping, Seller provided a spreadsheet identifying well completion intervals for Seller MW Nos. 1, 2, 4 and 9; DWR has WCRs for DWR MWs. Also, per the DTIWT, Exhibit 1 does not provide locations or construction of third-party groundwater wells within the area of the transfer-related groundwater pumping. In Seller's 2013 water transfer proposal, p. 2 of the proposal cover letter states Seller is not aware of any contaminated areas that could be affected by the proposed transfer wells. In addition, Seller reviewed the State Water Board's GeoTracker website to identify sites with known water quality issues near the proposed transfer wells. GeoTracker identified 235 sites within 5 miles of the proposed transfer wells. Of these sites, 116 are closed, 19 are inactive, 2 are elible for closure, 38 are active, and 60 are permitted facilities. The nearest site is the located near the center of Seller. GeoTracker identifies that this site has undergone extensive remediation since 1999 and is being monitored. The remaining active sites are primarily located in nearby urban areas including Woodland and West Sacramento. Seller needs to provide an update to its 2013 findings to determine any changed conditions relative to contaminated areas. | See the updated 2014 Water Transfer map and Exhibit, which identifies two additional groundwater wells that will be relied upon for monitoring purposes in the areas suggested by Reclamation and DWR. No additional information for third-party wells is readily available. A review of the State Water Resources Control Board's GeoTracker website identified no new sites have been identified within a 5-mile radius of the transfer well. | Seller's responses satisfy this requirement. However, the Agencies need to receive the WCR's for these 2 additional monitoring wells (MW-CCSB1 and MW-SE1). Also, on the revised Draft Exhibit 1, Table 3, please remove the listings for 08N03E04R001M and 10N02E12R001M since these wells were destroyed and have been removed from the monitoring program. | Seller does not have WCR's for the two additional monitoring wells (MW-CCSB1 and MW-SE1). Please see the revised updated Exhibit 1 , Table 3. | Seller satisfies this requirement. However, we request that Seller visit MW-CCSB1 and MW-SE1 to obtain at least some basic well construction information (e.g., tag the well bottom for depth, casing diameter, obtain photos, etc.).
GW Pumping Measurements | Yes | Exhibit 1 states Seller will record and report the instantaneous and cumulative (i.e., totalizer) flow meter measurements in accordance with the schedule specified in the DTIWT. |  | --
Groundwater Level Measurements | Yes | Exhibit 1 provides a schedule of groundwater level measurements for the proposed transfer and monitoring wells that is consistent with the DTIWT. |  | --
Groundwater quality monitoring | Yes | Exhibit 1 states specific conductance will be monitored at the proposed transfer wells and reported at the frequency specified in the DTIWT. |  | --
Land subsidence detection or credible analysis | Incomplete | Exhibit 1 states the proposed groundwater extraction constitutes a small fraction of the seasonal groundwater extraction for this area and is not considered to pose a significant potential risk of land subsidence. Exhibit 1 states DWR will continue to monitor the potential for land subsidence within the project area through evaluation of data from nearby extensometers, including periodic re-surveying of the Sacramento Valley GPS Land Subsidence Network. However, recent measurements by DWR at their extensometer located near the center of Seller's Property indicates that increased land subsidence occurred in 2013. To address this issue, a subsidence monitoring plan is currently being formulated by Seller in collaboration with Reclamation. Seller’s Proposal must acknowledge the current subsidence concerns at Seller's Property and incorporate the final subsidence monitoring plan into its overall water transfer monitoring plan. | See the subsidence monitoring elements contained in the forbearance agreement between Seller, Reclamation, and the Tehama-Colusa Canal Authority. | Seller's responses satisfy this requirement.
Coordinated data collection and cooperation with other monitoring efforts in the area | Yes | Exhibit 1 states Seller shall coordinate the collection and organization of monitoring data and has identified the point of contact as: |  | --
Data evaluation and reporting | Yes | Seller will submit monthly data summary tables to Reclamation reporting groundwater level and water quality data collected. Also, a final project summary report will be submitted to Reclamation no later than May 31, 2015. Exhibit 1 identifies elements that will be included in the final report, which are consistent with those specified in the DTIWT. |  | --
Groundwater Substitution Transfer Mitigation Plan
Required Elements of Plan | Meets Requirement(s) | Comments |  | Reclamation Responses to Additional Information Provided
Procedure for seller to receive reports of purported effects and report information to DWR, Reclamation and local agencies | Yes | The Mitigation Plan (Plan) states Seller will identify a contact person or persons who will be responsible for initially reponding to a notification of a potential Third Party impact. Upon receiving notification of a potential Third Party impact, Seller will contact the Third Party within 5 business days and obtain all available information regarding the nature and extent of the potential impact, and provide that information to Reclamation and the Department of Water Resources (DWR) within 10 business days. Seller will regularly update Reclamation and DWR on the status of Third Party impact concerns. |  | --
Procedure for investigating any purported effect with a means to resolve disputes between seller and other parties claiming injury | Yes | After the relevant information regarding the potential impact has been received, Seller will develop an approach to: (a) determine whether the Third Party has actually been impacted by groundwater pumping performed for the 2014 Water Transfer, and, if so; (b) mitigate for the impact. Seller will coordinate with Reclamation and DWR in developing the foregoing approach within 20 business days of contacting the Third Party. |  | --
Development of mitigation options, in cooperation with the affected third parties, for legitimate effects | Yes | Actions that may be taken to mitigate an impact include, but are not limited to: reduction in hours of groundwater pumping per day at one or more of Seller’s participating transfer wells, cessation of groundwater pumping at one or more participating groundwater wells, or other reasonable measures determined to be appropriate by Seller. |  | --
Assurance that adequate financial resources are available to cover reasonably anticipated mitigation needs | Yes | The statement in the Plan, "Seller will promptly mitigate any Third Party impacts that are reasonably likely to have been caused by groundwater pumping under the 2013 (now 2014), Water Transfer." addresses this required element. |  | --
Notes:
APPLICANT PROVIDED SUFFICIENT INFORMATION:
NEEDS FURTHER INFORMATION (REQUIRED):
NEEDS FURTHER INFORMATION (IF AVAILABLE):
1Source: The required information stated above was summarized from the document titled Draft Technical Information for Preparing Water Transfer Proposals, October 2013 (DTIWT).